## Sheet1
TaskID | Task Name | Owner | Task Assigned to | Start Date | End Date | Status
1 | Understanding requirements | Lockers | Heera P | 2022-03-31 | 2022-03-31 | Completed
2 | Design flowchart and Write Algorithm | Lockers | Heera P | 2022-04-01 | 2022-04-01 | Completed
3 | Design classes | Lockers | Heera P | 2022-04-02 | 2022-04-02 | Completed
4 | Develop code | Lockers | Heera P | 2022-04-03 | 2022-04-06 | Completed
5 | Tetsing | Lockers | Heera P | 2022-04-03 | 2022-04-06 | Completed
6 | Pushing code to GitHub | Lockers | Heera P | 2022-04-07 | 2022-04-07 | Completed